## Sheet1
TIME | ACTIVITY | VOLUNTEERS
8:00 | Bring backpacks, set up signs to identify seating area for large group | 6
8:30 | Set up chairs/signs and snacks at reading stations
| Set up PA system and chairs on stage | Peter Cahn/ Rob Wallace
9:00 | Greeters- Rotarians chat with celebrity readers | 12
9:15 | Buses picks up kids from schools
9:30 | Buses arrive (Music starts)
Characters wave and welcome children
9:45 | Rotarian Greeters walk kids to color groups on grass
10:00 | Welcome from Dr. White and Dr. Ortiz…. (Who will MC this event?)
10:10 | John Jorgenson- Good Queen Sue
10:20 | Sandy Holman- We All Have Heritage
10:30 | Pass out book bags (Rotarians)
10:35 | Open Book Bags
10:45 | Move to celebrity reading groups (12 each- led by characters)
10:50 | Story telling and Snack
11:15 | Rotarians walk kids to bus
11:30 | Buses leave- Characters wave as they go
11:30-12:00 | Clean Up | 6